## ProjectSchedule
Project: TextYourIoTDevice
|  | Project Start: | 2024-10-21
|  | Today: | 2025-02-21
|  | Display Week: | 1 |  |  | 2024-10-21 | [6 empty] | 2024-10-28 | [6 empty] | 2024-11-04 | [6 empty] | 2024-11-11 | [6 empty] | 2024-11-18 | [6 empty] | 2024-11-25 | [6 empty] | 2024-12-02 | [6 empty] | 2024-12-09 | [6 empty] | 2024-12-16 | [6 empty] | 2024-12-23 | [6 empty] | 2024-12-30 | [6 empty] | 2025-01-06 | [6 empty] | 2025-01-13 | [6 empty] | 2025-01-20 | [6 empty] | 2025-01-27 | [6 empty] | 2025-02-03 | [6 empty] | 2025-02-10 | [6 empty] | 2025-02-17
 | time axis 2024-10-21 to 2025-02-23
TASK | Description | PROGRESS | START | END | DAYS | bar: 2024-10-21 to 2025-02-23
Phase 1: Organization
Team building | Select topic, discuss tasks | 100% | 2024-10-21 | 2024-10-28 | 8
Organization | Set goals, discuss milestones, create sharepoint for saving files | 100% | 2024-10-21 | 2024-11-04 | 15
GitHub Repository | Create GitHub Repository | 100% | 2024-10-21 | 2024-10-28
Phase 2: Submission and presentation of your architecture
Collect the requirements and discuss about additional requirements |  | 100% | 2024-10-28 | 2024-11-25 | 29
Survey the solution space | IoT-Hardware-Plattformen, Sensoren, Kommunikationsprotokolle, Sicherheitsmechanismen, Instant Messenger API | 100% | 2024-10-28 | 2024-11-25 | 29
Systemarchitektur | Sensorebene, Kommunikationsschicht, Grenzrouter und Gateway, Grenzrouter und Gateway, Remote Access Service | 70% | 2024-10-28 | 2024-11-25 | 29
Discuss about software development model | Select a software development model | 100% | 2024-10-28 | 2024-11-25
Preparing a presentation | - | 100% | 2024-10-28 | 2024-11-25
Researching Tools and Protocols | required tools and protocols with selection criteria and arguments | 100% | 2024-10-28 | 2024-11-25
Preparing AWS Cloud and Services | EC2, AWS IoT Core, Lambda, etc. | 100% | 2024-10-28 | 2024-11-25 | 29
Create a firmware based on RIOT | Run RIOT on Microproccessors and test it | 100% | 2024-10-28 | 2024-11-25
Phase 3: Present your walking skeleton (incl. demo)
Preparing a presentation | - | 100% | 2024-11-25 | 2025-01-20 | 57
Create a walking skeleton | Development and deployment | 100% | 2024-11-25 | 2025-01-20 | 57
fulfillment of the requirements | Functional and Non-Functional requirements | 80% | 2024-11-25 | 2025-01-20 | 57
Systemarchitektur | Determination of the final architecture version | 100% | 2024-11-25 | 2025-01-20 | 57
Create a demo | Create a video | 100% | 2024-11-25 | 2025-01-20
Development tests and bug fixes | Provision of a working version | 100% | 2024-11-25 | 2025-01-20
Discussion about next steps | Fulfillment of the requirements, Improvement and completion, etc. | 100% | 2024-11-25 | 2025-01-20 | 57
Phase 4: Presentation | Give a short presentation on your work (live demo?)
Preparing a presentation | - | 100% | 2025-01-20 | 2025-02-10 | 22
Preparing a live demo | - | 100% | 2025-01-20 | 2025-02-10 | 22
fulfillment of the requirements | Functional and Non-Functional requirements | 90% | 2025-01-20 | 2025-02-10 | 22
Improvement and completion | Source code and decumentation | 70% | 2025-01-20 | 2025-02-10 | 22
Clean up, organize, and review | The repository | 80% | 2025-01-20 | 2025-02-10
Phase 5: Submission | Final version of the code is in the repository, You have granted access to me, Send me your documentation
Improvement and completion | Source code | 100% | 2025-02-10 | 2025-02-21 | 12
fulfillment of the requirements | Functional and Non-Functional requirements | 100% | 2025-02-10 | 2025-02-21 | 12
Clean up, organize, and review | Source code and the repository | 100% | 2025-02-10 | 2025-02-21 | 12
Grant access to Prof | GitHub | 0% | 2025-02-10 | 2025-02-21 | 12
Final version of the code in the repository | - | 100% | 2025-02-10 | 2025-02-21
Final version of the documentation | - | 0% | 2025-02-10 | 2025-02-21
2018-01-13
Note on G6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
► Watch How This Gantt Chart Was Created
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.